## Sheet1
ISO/IEC JTC 1/SC 22/WG 23 N 0341
Schedule for the preparation of TR 24772, Edition 2
Prepared by Jim Moore
2011-06-19
Start date | # of Days | End date | Activity or Event
|  | 2010-12-16 | End of meeting #16
2010-12-16 | 97 | 2011-03-23 | Editor prepares revision of base document. Liaisons prepare revision of annexes
2011-03-23 | 2 | 2011-03-25 | Meeting #17. Review revised baseline document and revised annexes
2011-03-25 | 37 | 2011-05-01 | Editor assembles entire document and circulates for formal WD review
2011-05-01 | 30 | 2011-05-31 | Detailed review of document by WG 23 participants
2011-05-31 | 0 | 2011-05-31 | DEADLINE FOR SUBMISSION OF WRITTEN COMMENTS
2011-05-31 | 19 | 2011-06-19 | Editor prepares recommended disposition of comments
2011-06-19 | 1 | 2011-06-20 | Meeting #18. Discussion of comments
2011-06-20 | 30 | 2011-07-20 | Editor prepares draft and circulates for formal WD review
2011-07-20 | 30 | 2011-08-19 | Detailed review of document by WG 23 participants
2011-08-19 | 47 | 2011-10-05 | Editor prepares recommended disposition of ballot comments
2011-10-05 | 2 | 2011-10-07 | Meeting #20. Discussion of comments
2011-10-07 | 23 | 2011-10-30 | Editor prepares draft and circulates for formal WD review
2011-10-30 | 30 | 2011-11-29 | Detailed review of document by WG 23 participants
2011-11-29 | 15 | 2011-12-14 | Editor prepares recommended disposition of comments
2011-12-14 | 2 | 2011-12-16 | Meeting #21. Discussion of comments.
2011-12-16 | 30 | 2012-01-15 | Editor prepares draft for PDTR ballot
2012-01-15 | 15 | 2012-01-30 | Editor submits draft for ballot and Secretariat begins the ballot
2012-01-30 | 90 | 2012-04-29 | Duration of ballot. Note that Meeting #22 occurs during the ballot
2012-04-29 | 41 | 2012-06-09 | Editor prepares recommended disposition of ballot comments
2012-06-09 | 2 | 2012-06-11 | Estimated date of Meeting #23. Disposition of ballot comments
2012-06-11 | 30 | 2012-07-11 | Editor prepares draft for 2nd PDTR ballot
2012-07-11 | 15 | 2012-07-26 | Editor submits draft for ballot and Secretariat begins the ballot
2012-07-26 | 90 | 2012-10-24 | Duration of ballot. Note that Meeting #24 occurs during the ballot
2012-10-24 | 41 | 2012-12-04 | Editor prepares recommended disposition of ballot comments
2012-12-04 | 2 | 2012-12-06 | Estimated date of Meeting #25. Disposition of ballot comments
2012-12-06 | 30 | 2013-01-05 | Editor prepares draft for DTR ballot
2013-01-05 | 15 | 2013-01-20 | Editor submits draft for ballot and Secretariat begins the ballot
2013-01-20 | 90 | 2013-04-20 | Duration of ballot. Note that Meeting #26 occurs during the ballot
2013-04-20 | 45 | 2013-06-04 | Editor prepares recommended disposition of ballot comments
2013-06-04 | 2 | 2013-06-06 | Estimated date of Meeting #27. Disposition of comments
2013-06-06 | 30 | 2013-07-06 | Editor prepares draft for publication
2013-07-06 | 60 | 2013-09-04 | Editor collaborates with ISO staff editor on final manuscript
2013-09-04 | 60 | 2013-11-03 | TR 24772 Edition 2 is published
Formulas:
Start date = [End date, row above]
End date = [Start date]+B8